Grande finale Cross Border Show!

Medway.

2013

2014

2012

Building on young peoples skills and confidence at local level to get them to a standard for cross border shows.

Oct - Medway WP3 Workshops & Cross Border Talent Show

Small Community Talent Show in Suffolk/Medway/

Pas De Calais/Brest(2)

April – Cross Border Workshop, Pas De Calais

July - Suffolk Host 4 Day Workshop

All partners exchange acts through video and create a Cyber Cross Border Talent Show.

Feb – Cross Border preparation Workshop, Brest

YP exchange & help deliver community show

Arque Talent Show

April – Annual Talent Show event, Brest

2015

Work Package 3 Timeline

2012 - 2015

Project Targets 2012 – 2015

- Minimum of 470 local workshops (18 per partner per year)

- Monthly Cyber Session – 30 Mandatory & 25 Drop in

- Minimum of 10 Talent Shows